## Timeline
Illustrative CIP Process Timeline
Customize this template by changing dates, editing or adding actions, and changing due dates.
Actions | time axis 2014-09-29 to 2015-08-10
Key meetings
Project launch—in-country | bar: 2014-09-29
National Family Planning Technical Working Group—meeting #1 | bar: 2014-10-06
National Family Planning Technical Working Group—meeting #2 | bar: 2015-01-05
National Family Planning Technical Working Group—meeting #3 | bar: 2015-04-06
National Family Planning Technical Working Group—meeting #4 | bar: 2015-07-06
Plan launch | bar: 2015-08-03
Step
PHASE 1: PLAN
Step 1: Obtain Buy-in and Secure Resources for CIP Development
Activity 1A: Arrive at decision to engage in the CIP process | bar: 2014-09-29
Activity 1B: Establish a CIP Task Force | bar: 2014-10-06
Activity 1C: Secure financial and human resources for CIP development | bar: 2014-10-13 to 2014-10-20
Activity 1D: Make a formal request for CIP support | bar: 2014-10-20 to 2014-11-03
Step 2: Prepare for CIP Development
Activity 2A: Form a CIP Technical Support Team | bar: 2014-11-03
Activity 2B: Define the CIP development process and timeline | bar: 2014-11-03 to 2014-11-17
Activity 2C: Identify key family planning stakeholders | bar: 2014-11-03 to 2014-12-08
Activity 2D: Kick-off the CIP development process | bar: 2014-12-15
PHASE 2: DEVELOP
Step 3: Conduct a Situational Analysis
Activity 3A: Gather information on the current family planning context, programs, and resources | bar: 2014-12-22 to 2015-01-12
Activity 3B: Conduct information review, synthesis, and analysis | bar: 2015-01-05 to 2015-01-19
Activity 3C: Prioritize issues and analyze root causes | bar: 2015-01-26 to 2015-02-02
Step 4: Formulate a Technical Strategy and Implementation Plan
Activity 4A: Set or refine the family planning goal | bar: 2015-02-16
Activity 4B: Define results and prioritize outcomes and interventions | bar: 2015-02-23 to 2015-03-09
Activity 4C: Validate the results chain and strategic priorities | bar: 2015-03-16 to 2015-03-23
Activity 4D: Select indicators and estimate targets | bar: 2015-03-02 to 2015-03-23
Activity 4E: Develop implementation plan with activities and sub-activities | bar: 2015-03-30 to 2015-04-13
Activity 4F: Refine and validate technical strategy | bar: 2015-03-23 to 2015-04-27
Activity 4G (optional): Align with the subnational level | bar: 2015-04-27 to 2015-05-04
Activity 4H (optional): Estimate impact | bar: 2015-02-09 to 2015-02-16; 2015-04-13 to 2015-04-20; 2015-05-11 to 2015-05-18
Step 5: Estimate Costs and Resource Gap and Iterate Technical Strategy
Activity 5A: Estimate common unit costs | bar: 2015-04-06 to 2015-04-20
Activity 5B: Input quantity of units required to achieve plan objectives | bar: 2015-04-13 to 2015-05-11
Activity 5C: Review and validate cost estimates | bar: 2015-05-04 to 2015-05-18
Activity 5D: Conduct CIP financial gap analysis | bar: 2015-05-25 to 2015-06-08
Activity 5E: Realign technical strategy to ensure reasonable cost | bar: 2015-06-08 to 2015-06-22
Activity 5F: Revise and validate final cost and resource gap | bar: 2015-06-29
Step 6: Finalize Institutional Arrangements for Execution
Activity 6A: Define a stewardship and accountability structure | bar: 2015-06-29 to 2015-07-13
Activity 6B: Define coordination mechanisms | bar: 2015-07-13
Activity 6C: Identify capacity development and implementation support needs | bar: 2015-07-20 to 2015-07-27
Step 7: Secure Final Approval and Launch the CIP
Activity 7A: Review and approve the CIP | bar: 2015-07-06
Activity 7B: Develop a dissemination plan and materials | bar: 2015-06-22 to 2015-06-29
Activity 7C: Produce and print the final document | bar: 2015-07-13 to 2015-07-27
Activity 7D: Hold a launch event and dissemination activities | bar: 2015-08-03 to 2015-08-10
PHASE 3: EXECUTE
Step 8: Provide Effective Stewardship for CIP Execution
Activity 8A: Implement effective and efficient coordination mechanisms | 2015-08-10: -->
Activity 8B: Lead and manage the execution process | 2015-08-10: -->
Activity 8C: Integrate CIP into existing annual work planning, or if necessary, develop annual joint workplans | 2015-08-10: -->
Activity 8D: Engage at the subnational level to facilitate the execution of the CIP | 2015-08-10: -->
Step 9: Design and Implement Performance Monitoring Mechanisms | 2015-08-10: -->
Activity 9A: Set up performance monitoring tools and process | 2015-08-10: -->
Activity 9B: Regularly collect performance data | 2015-08-10: -->
Activity 9C: Hold regular performance reviews | 2015-08-10: -->
Activity 9D: Review and revise | bar: 2015-08-10
Activity 9E: Conduct a CIP end-line review | bar: 2015-08-10
Step 10: Conduct Continuous Resource Mobilization | 2015-08-10: -->
Activity 10A: Mobilize resources for the CIP | bar: 2015-08-10
Activity 10B: Conduct family planning budget tracking | 2015-08-10: -->
Activity 10C: Regularly update the financial gap analysis | bar: 2015-08-10
Activity 10D: Conduct ongoing advocacy | 2015-08-10: -->